Agenda for 1 February 2006 Telecon

Room:  802     10 a.m. - 1 p.m. EST

10:00-10:10            Introduction: Review of action items from December telecon (Toth, Lefaivre)

SPRING OPERATIONAL IMPLEMENTATION

10:10-10:25            Operational data exchange

a) Grib2 status (Wobus, Pelletier, Gordon/Michaud)

b) Reliability and speed of data transfer (Gordon/Michaud, Pelletier)

10:25-10:40            Bias correction: status of implementation (Cui, Verret)

10:40-10:55            Climate anomaly product: status of implementation (Zhu, Verret)

10:55-11:10            Week 2 product development (O'lenic, Rosengaus)

11:10-11:25            NMSM considerations

a)  Graphical products on the web (Jacobs)

b)  Other issues (Toth, Rosengaus)

11:20-11:45            Coordination of operational implementation (Toth/Michaud, Lefaivre)

FUTURE PLANS

11:45-11:55            Discussion on schedule of future research/development/expansion (Toth, Lefaivre)

11:55-12:10            Statistical post-processing plans (bias correction, weights, climate anomalies, etc) (Verret, Toth)

12:10-12:20            Wave, river flow, etc “downstream” applications (Chen/Toth, Wilson?)

12:20-12:35            FNMOC/AFWA expansion

a) Data exchange

b)  Post-processing arrangements

12:35-12:45   UK Metoffice developments/plans

12:45-12:55            Spring workshop

12:55-13:00            Next telecom

Dec 13, 2005 Telecon

ACTION ITEMS

1)        Draw up plans for generation  of 06Z & 18Z “control” analysis at MSC & transmission to NCEP (28 Dec, Yves Pelletier – Dick Wobus)

2)         Decide which NCEP CDAS (to connect with reanalysis climatology) analysis to use (2-day old or near-real time) and prepare plan for real time transmission to MSC (28 Dec, Dick Wobus/Dave Michaud – Richard Verret)

3)         Provide statistics on fit of 30yr raw mean to 4-component Fourier smoothed climatological mean (28 Dec, Yuejian Zhu – Richard Verret)

4)         NCEP prepares implementation notice 90 days in advance (expected by mid-Febr, Brent Gordon)

5)         NCEP provides GRIB1, GRIB2 sample data and GRIB converter software (Jan 5, Richard Wobus – Yves Pelletier)

6)         Assess realiability / fault rate of current ftp data connection (15 Jan, Brent Gordon – Yves Pelletier)

7)         Provide initial cost estimate (to be shared by MSC/NWS) of direct link (15 Jan, Yves Pelletier)

8)         Spring workshop plans confirmed (Dec 22, Z. Toth – L. Lefaivre)

NOTES

1)         MSC new implementation

2)          Equal weights used as default for Spring implementation; Correlation method for weights dropped; NCEP favors “best member” or similar statistics; will compare with MSC Bayesian and other potential methods

3)          Agreed to use mean of MSC/NCEP analysis when determining weights

4)          Colleague of Laurie Wilson plans to talk with Roman Krzystofowicz about Baysean ideas

5)          Decided to synchronize operational implementations related to the data transfer only; other implementations coordinated less strictly (+/- 15/30 days)

6)          Possible need/costs for direct link should be considered for operational data exchange

7)          FNMOC ready for initial data exchange by February

8)          AFWA wants raw (not post-processed) data, will get MSC data directly from MSC

9)          FNMOC to implement ET technique, forecasts out to 15 days, and increased resolution OR twice a day ensemble in spring

10)      UK Metoffice proposes to exchange data through TIGGE – this allows only research applications

11)      Next meeting proposed for 24-25 Jan

12)      NCEP plans to implement wave ensemble in spring/summer

AUDIO PARTICIPANT ACCESS

| CALL DATE: | FEB-01-2006 (Wednesday) |
| --- | --- |
| CALL TIME: | 10:00 AM EASTERN TIME |
| DURATION: | 4 hr |
| LEADER: | MR ZOLTAN TOTH |
| USA Toll Free Number: | 800-857-5086 |
| USA Toll Number: | +1-210-234-0031 |

PASSCODE: 18174

For security reasons, the passcode and the leader's name will be required to join your call.

IN-CONFERENCE FEATURES

The following features are available for you to use on your phone during an active conference:

- Press *0 operator assistance (small fee may apply). - Press *6 mute/unmute individual line.