THORPEX-HYDRO Project

March 25, 2008

Project Team

- NCEP/EMC and its THORPEX and other collaborators - Zoltan Toth, NCEP Project Leader

- OHD and its collaborators - DJ Seo, OHD Project Leader

Partners

HMT – Tim Schneider, Program Manager (ESRL)

Test experimental hydrometeorological products in HMT testbeds; Provide feedback for product/service development efforts

ESRL/GSD – Paul Schultz, Group Leader

Develop methods for downscaling coarser resolution ensemble forecasts to NDFD resolution (precipitation, temperature, etc.)

University of Virginia – Roman Krzysztofowicz, Professor

Develop statistical bias correction algorithms and codes

HPC – QPF/HMT Desks, Ed Danaher (NCEP/HPC)

Provide guidance and advice on interpretation and use of hydrometeorological ensembles in high impact forecast situations on operational basis

National Precipitation Verification Unit (NPVU)

Coordinate PQPF verification activities

CPPA Core Project – Pedro Restrepo, John Schaake (OHD) and Ken Mitchell (NCEP)

Interface with land surface and hydrologic modeling capabilities designed for seasonal applications

Introduction

This document summarizes a 2-year work plan with an outlook beyond FY09 for the joint effort between the THORPEX program and the Hydrology Program, in collaboration with the Hydrometeorology Testbed (HMT) Program and the Climate Prediction Program for the Americas (CPPA), to produce reliable and skillful ensemble forecasts of hydrometeorological variables at the weather scale, in particular for high-impact events. The targeted users are the NWS River Forecast Centers (RFC) for operational hydrologic ensemble forecasting via the eXperimental Ensemble Forecast System (XEFS) and the water resources managers and end users for various hydrology and water resources applications.

Overarching Goals

- Accelerate development of reliable and skillful hydrometeorological (precipitation, temperature and potential evaporation) ensemble forecast products for hydrology and water resources applications

- Fast-track infusion of new and improved hydrometeorological ensemble and probabilistic guidance products into the RFC operations through the eXperimental Ensemble Forecast System (XEFS)

Objectives

- Develop and operationally implement real-time bias correction, downscaling and hindcasting techniques that are applicable to global, regional, and climate ensembles

- Develop capabilities for routine ingestion, testing, and use in XEFS of NCEP ensembles by OHD and RFCs

- Improve land surface modeling capabilities for large-scale hydrologic evaluation of hydrometeorological ensembles at the weather scale and for collaborative research and development of hydrologic ensemble techniques and products that may best utilize them

- Enhance capabilities for seamless verification of hydrometeorological and hydrologic ensembles across NCEP, OHD and RFCs

Fig 1 THORPEX-HYDRO Project – Overarching Goals

Tasks and Milestones

Objective 1: Develop and operationally implement real-time bias correction, downscaling and hindcasting techniques that are applicable to global and regional ensembles.

Tasks

- Accelerate development, testing, evaluation and operational implementation of the Bayesian ensemble processor (BEP), developed jointly with Roman Krzysztofowicz. In tests, a single-value (not ensemble) forecast version of his algorithm outperformed NWS MOS for precipitation forecasting.

- Collaborate with NCEP/CPC and OHD on best observational 6-hourly precipitation analysis (CPC global precipitation analyses for global, NWS-operational gage-radar estimates for CONUS).

- Collaborate with GSD/ESRL on conversion of zero forecast precipitation into “pseudo-precipitation” values. This conversion will make precipitation a continuous variable, facilitating the use of a uniform BEP for all variables.

- Collaborate with Krzysztofowicz on developing and porting Bayesian algorithms and codes for use at NCEP.

- Operationally implement BEP for 6-hourly precipitation for the NAEFS ensemble system.

- Develop, evaluate and, if determined operation-ready, implement the real-time hindcast generation algorithm.

- Facilitate use of hindcast data in BEP.

- Collaborate with GSD/ESRL in their development and testing of precipitation downscaling algorithms.

- Test and evaluate bias-corrected and downscaled precipitation forecasts in hydrologic applications at OHD and EMC through:

  - Global river flow ensemble experiments at EMC, and

  - XEFS at OHD.

FY08-09 Milestones

- December 2007 – Implement NAEFS forecasts downscaled to 5x5 km NDFD grid over CONUS (6-hrly output to 16 days based on global NCEP high-resolution control and ensemble plus Canadian ensemble for 2m temp, 10m u/v wind, mean sea level pressure).

- Summer 2008 – Implement downscaled NAEFS forecasts for Alaska domain, including additional new near-surface variables also for CONUS (2m min/max & dewpoint temp, 10m wind speed and direction).

- Fall 2008 – Implement stochastic perturbations into ensemble integrations as well as increase resolution for global and regional ensembles and/or introduce hindcasts for ensemble control.

- Spring 2009 – Implement climatological downscaling for NAEFS precipitation forecasts over CONUS. Complete downscaling of precipitation from model grid to NDFD grid using global CPC global precipitation analysis datasets with operational NWS gage and radar-based 6-hr analysis fields inserted over CONUS.

- Fall 2009 – Implement BEP for 6-hr precipitation forecasts for NAEFS and SREF on model grids to reduce systematic errors in ensemble distribution.

Prospective Milestones Beyond FY09

- Spring 2010 – Include FNMOC and ECMWF ensembles into NAEFS.

- Fall 2010 – Increase resolution for global and regional ensembles. Implement hindcast system that uses the latest version of the data assimilation and numerical modeling system, allowing high-quality bias correction of precipitation and river flow.

- Spring 2011 – Upgrade  6-hrly precipitation forecast downscaling with addition of stochastic processes.

- Fall 2011 – Apply BEP on all model variables on model grids for NAEFS & SREF ensembles, including potential evapotranspiration.

- Spring 2012 – Produce probabilistic/ensemble guidance based on a suite of available numerical guidance. Merge and bias-correct information from global and regional high-resolution control and ensemble forecast systems (NAEFS, GFS, NAM, SREF). Establish bias-corrected ensemble forecast database consistent with best available probabilistic guidance. Back-propagate value-added changes made by forecasters into numerical ensemble guidance database.

- Fall 2012 – Add new downscaled variables with use of SMARTINIT, including potential evapotranspiration, for 5x5 km or higher resolution output.

- Spring 2013 – Introduce feature-based bias corrections.

Objective 2: Develop capabilities for routine ingestion, testing, and use of NCEP ensembles by OHD and RFCs.

Tasks

- Develop capabilities at OHD and RFCs to process and evaluate NCEP prototype ensemble products.

- Provide access to and tools for using operational and experimental NCEP ensemble products in XEFS.

- Provide feedback to NCEP to influence future development, testing and implementation of ensemble forecast systems, products and services.

FY08-09 Milestones

- Dec 2007 – Make available individual ensemble members by adding downscaling vector and coarse resolution member data (20 members per cycle, 80 per day from NCEP, 40 members from Canada):

- Engage and collaborate with OHD and RFCs in ongoing evaluation.

- Explore testing in winter season at some RFCs in collaboration with HMT.

- May 2008 – Produce downscaled temperature information on 5x5 km NDGD grid, 4 times/day 6-hourly output, from NAEFS ensemble, out to 16 days:

- Products include mean, mode of ensemble, values for 10, 50, 90 percentile ensemble distribution.

- Sep 2008 – Demonstrate capabilities to ingest and process NCEP ensembles for XEFS prototype development at OHD and experimental use with ESP at an RFC.

- Sep 2009 – Carry out comparative evaluation of NCEP ensembles for prognostic verification.

Prospective Milestones beyond FY09

- Implement in the Ensemble Pre-Processor III (EPP3) of XEFS capabilities for ingest and processing of NCEP ensembles.

- Carry out joint analysis of multiscale and multimodel ensembles for development of blending and merging procedures in EPP3.

Objective 3: Improve land surface modeling capabilities for large-scale hydrologic evaluation of hydrometeorological ensembles at the weather scale and for collaborative research and development of hydrologic ensemble techniques and products that may best utilize them.

The tasks under this objective heavily leverage the CPPA Core Project.

Tasks

- Improve capabilities for CONUS-wide hydrologic evaluation of hydrometeorological ensembles:

- Start testing hindcasts when available.

- Use ensembles from the gridded Ensemble Pre-Processor (EPP) as comparative reference.

- Improve land surface and river routing model components.

- Verify streamflow ensemble results against observed flow.

- Include and improve post processing for accounting of hydrologic uncertainty.

- Include DA component.

- Transfer/adapt OHD/RFC and community hydrologic modeling capabilities to facilitate testing over CONUS and global domains:

- OHD high resolution river routing model over CONUS.

- Alternative land surface models (funded via CPPA).

- Develop/test methods to represent uncertainty related to land surface and hydrologic modeling

- Develop/test methods for assimilation of land surface and hydrologic observations

- Develop/test statistical methods to represent hydrologic uncertainty due to water management decisions

- Develop global ensemble hydrologic prediction capability at NCEP:

- Run as part of NCEP suite

- Initially for international use

- In the future for possible operational use

- Initially focus on large rivers.

# FY08-09 Milestones

- Sep 2008 – Demonstrate capability for large-scale evaluation of precipitation and streamflow ensembles using improved land-surface and routing model components.

- Sep 2009 – Carry out large-scale comparative evaluation of streamflow ensembles forced by the GFS and gridded EPP-generated precipitation and temperature ensembles.

Objective 4: Enhance capabilities for integrated verification of hydrometeorological and hydrologic ensembles across NCEP/EMC, NCEP/HPC, OHD, RFCs, and NPVU.

Tasks

- Coordinate and leverage ensemble verification efforts at OHD and NCEP for integrated systematic diagnostic verification of hydrometeorological and hydrologic ensembles.

- Develop ensemble/probabilistic verification products and context information for NCEP hydrometeorological ensembles for use in XEFS.

- Demonstrate and quantify marginal value of improvement in hydrometeorological ensembles to hydrology and water resources applications.

.

FY08-09 Milestones

Sep 2008 – Develop a science strategy for integrated ensemble verification across weather and water predictions. Identify candidate verification measures and supplemental information, including multiscale verification information that may be passed across NCEP, OHD and RFCs for diagnostics and for operational hydrologic forecasting via XEFS.

Sep 2009 – Jointly carry out basic integrated verification of operational and experimental hydrometeorological and hydrologic ensemble forecasts and quantify the margin of improvement.

Prospective Milestones Beyond FY09

Sep 2010 - Evaluate ensemble precipitation forecasts for various accumulation periods and various size areas to facilitate hydrologic interpretation of the results.

Sep 2011 – Evaluate ensemble hydrologic forecasts against river gage observations.